## Gantt Chart PBL
GANTT CHART TIMELINE PROYEK PBL – JADWALIN
B2B Smart Shift Scheduling Platform ¦ D4 Teknik Informatika - Semester 5 Polinema
Tim Pengembang: Muhammad Farras A.A (PM/Backend), Umi Maharani (Full-Stack), Neyza Ratu Anastasya (UI/UX), Muhammad Yusuf (Database)
Sinkronisasi Jira Cloud PBL: 14 Oktober 2026 ¦ Total Tiket: 34 Task (23 Selesai, 1 Dalam Proses, 10 Terjadwal)
No | Key Jira | Nama Tugas / Task Description | Modul / Komponen | Penanggung Jawab (Assignee) | Prioritas | Mulai | Selesai | Durasi | Status | Progress | M1 (Sep W1) | M2 (Sep W2) | M3 (Sep W3) | M4 (Sep W4) | M5 (Okt W1) | M6 (Okt W2) | M7 (Okt W3) | M8 (Okt W4) | M9 (Nov W1) | M10 (Nov W2) | M11 (Nov W3) | M12 (Nov W4) | M13 (Des W1) | M14 (Des W2) | M15 (Des W3) | M16 (Des W4)
FASE INISIASI, ANALISIS KEBUTUHAN & SETUP SISTEM (Minggu 1 - 4)
1.1 | PBL-1 | Pembuatan ERD (Entity Relationship Diagram) | Database | Muhammad Farras A.A | Medium | 2026-09-01 | 2026-09-07 | 7 Hari | Done | 100%
1.2 | PBL-2 | Drafting UI/UX & Wireframe Awal | UI/UX | Neyza Ratu Anastasya | Medium | 2026-09-05 | 2026-09-15 | 11 Hari | Done | 100%
1.3 | PBL-3 | Finishing Proposal Proyek PBL & Persetujuan Dosen | Management | Umi Maharani | Medium | 2026-09-10 | 2026-09-18 | 9 Hari | Done | 100%
1.4 | PBL-4 | Inisialisasi Repository GitHub & Framework Laravel 12 | DevOps | Muhammad Farras A.A | Medium | 2026-09-12 | 2026-09-22 | 11 Hari | Done | 100%
1.5 | PBL-5 | Pembuatan Use Case Diagram & Flowchart Sistem | System Design | Muhammad Farras A.A | Medium | 2026-09-15 | 2026-09-23 | 9 Hari | Done | 100%
1.6 | PBL-6 | Finalisasi ERD Relasional (14 Entitas Lengkap) | Database | Umi Maharani | Medium | 2026-09-20 | 2026-09-25 | 6 Hari | Done | 100%
1.7 | PBL-7 | UI/UX Halaman Inti (Wireframe / Mockup Figma Mobile-First) | UI/UX | Neyza Ratu Anastasya | Medium | 2026-09-22 | 2026-09-28 | 7 Hari | Done | 100%
1.8 | PBL-12 | [Setup] Multi-Role Authentication & RBAC Middleware | Security / RBAC | Muhammad Farras A.A | High | 2026-09-24 | 2026-09-27 | 4 Hari | Done | 100%
1.9 | PBL-13 | [Setup] Base Layout Responsif & Brand Design System | UI/UX Layout | Umi Maharani | Medium | 2026-09-25 | 2026-09-28 | 4 Hari | Done | 100%
1.10 | PBL-14 | [Setup] Implementasi Database Migrations (14 Tabel) | Database | Muhammad Farras A.A | High | 2026-09-26 | 2026-09-29 | 4 Hari | Done | 100%
1.11 | PBL-15 | [Setup] Database Seeder Data Uji Coba Multi-Role | Database | Muhammad Yusuf | Medium | 2026-09-27 | 2026-09-30 | 4 Hari | Done | 100%
1.12 | PBL-16 | [Setup] Automated Test Suite Setup (23 Tests Passing) | QA / Test | Muhammad Farras A.A | Medium | 2026-09-28 | 2026-09-30 | 3 Hari | Done | 100%
SPRINT 1: FONDASI TEKNIS, MASTER DATA & TAMPILAN PUBLIK (Minggu 5 - 6)
2.1 | PBL-8 | Sprint 1 - [Core Engine] Implementasi Model Eloquent & Relasi Database (14 Entitas) | Core Engine | Muhammad Farras A.A | High | 2026-10-01 | 2026-10-07 | 7 Hari | Done | 100%
2.2 | PBL-9 | Sprint 1 - [Master Data] Modul CRUD Departemen & Posisi Jabatan | Master Data | Muhammad Yusuf | Medium | 2026-10-03 | 2026-10-10 | 8 Hari | Done | 100%
2.3 | PBL-26 | Sprint 1 - [UI/UX] Desain Landing Page Publik & Profil Akun | UI/UX | Neyza Ratu Anastasya | Medium | 2026-10-01 | 2026-10-10 | 10 Hari | Done | 100%
2.4 | PBL-11 | Sprint 1 - [Presensi] Modul Pencatatan Kehadiran Mandiri (Clock-In/Clock-Out) | Presensi | Umi Maharani | Medium | 2026-10-07 | 2026-10-14 | 8 Hari | Done | 100%
2.5 | PBL-39 | Sprint 1 - [Doc] Penyusunan Dokumen Spesifikasi Kebutuhan Perangkat Lunak (SKPL / SRS) | Documentation | Muhammad Farras A.A | High | 2026-10-05 | 2026-10-14 | 10 Hari | In Progress | 80%
SPRINT 2: KETERSEDIAAN, TEMPLATE SHIFT & CORE SCHEDULING (Minggu 7 - 9)
3.1 | PBL-24 | Sprint 2 - [Master] Pengaturan Dinamis Ketenagakerjaan (PP 35/2021) | Compliance | Muhammad Yusuf | Medium | 2026-10-15 | 2026-10-19 | 5 Hari | Done | 100%
3.2 | PBL-10 | Sprint 2 - [Availability] Form Input Jadwal Halangan Karyawan & Auto-Buffer | Availability | Neyza Ratu Anastasya | High | 2026-10-15 | 2026-10-23 | 9 Hari | Done | 100%
3.3 | PBL-18 | Sprint 2 - [Master] CRUD Template Shift Rutin & Kuota Posisi | Master Data | Muhammad Yusuf | Medium | 2026-10-17 | 2026-10-25 | 9 Hari | Done | 100%
3.4 | PBL-19 | Sprint 2 - [Availability] Panel Persetujuan Ketersediaan (Manager) | Availability | Neyza Ratu Anastasya | Medium | 2026-10-23 | 2026-10-28 | 6 Hari | Done | 100%
3.5 | PBL-17 | Sprint 2 - [Core] Algoritma Smart Scheduling Builder (Manager) | Core Engine | Muhammad Farras A.A | Highest | 2026-10-15 | 2026-10-28 | 14 Hari | Done | 100%
3.6 | PBL-21 | Sprint 2 - [Report] Rekapitulasi Timesheet & Ekspor Excel/PDF | Reporting | Umi Maharani | Medium | 2026-10-20 | 2026-11-02 | 14 Hari | Done | 100%
3.7 | PBL-21b | Review Kemajuan Sprint 2 & Konsultasi Dosen Pembimbing | Milestone | Muhammad Farras A.A | High | 2026-10-30 | 2026-11-02 | 4 Hari | To Do | 0%
SPRINT 3: PERTUKARAN SHIFT, OPEN SHIFT, NOTIFIKASI & OTOMATISASI (Minggu 10 - 12)
4.1 | PBL-22 | Sprint 3 - [Core] Dual-Mode Shift Swap & Transfer via Atomic Transaction | Shift Swap | Muhammad Farras A.A | High | 2026-11-03 | 2026-11-12 | 10 Hari | To Do | 0%
4.2 | PBL-25 | Sprint 3 - [Master] Manajemen Data Karyawan per Tim (Manager) | Management | Muhammad Yusuf | Medium | 2026-11-03 | 2026-11-10 | 8 Hari | To Do | 0%
4.3 | PBL-27 | Sprint 3 - [Presensi] Monitoring Kehadiran Realtime Tim & Toleransi Terlambat | Presensi | Umi Maharani | Medium | 2026-11-03 | 2026-11-14 | 12 Hari | To Do | 0%
4.4 | PBL-20 | Sprint 3 - [Notif] Pusat Notifikasi In-App Karyawan & Manager | Notification | Neyza Ratu Anastasya | Low | 2026-11-03 | 2026-11-14 | 12 Hari | To Do | 0%
4.5 | PBL-23 | Sprint 3 - [Core] Open Shift Broadcast & Pessimistic Locking Concurrency | Open Shift | Muhammad Farras A.A | High | 2026-11-08 | 2026-11-16 | 9 Hari | To Do | 0%
4.6 | PBL-38 | Sprint 3 - [UI/UX] Implementasi Role-Based Dashboard Operasional | UI/UX | Muhammad Yusuf | High | 2026-11-11 | 2026-11-22 | 12 Hari | To Do | 0%
4.7 | PBL-28 | Sprint 3 - [Presensi] Otomatisasi Penutupan Absensi (Auto Clock-Out Cron Job) | Automation | Umi Maharani | Medium | 2026-11-14 | 2026-11-21 | 8 Hari | To Do | 0%
SPRINT 4: QUALITY ASSURANCE, PENGUJIAN BEBAN & FINALISASI PROYEK (Minggu 13 - 16)
5.1 | PBL-29 | Sprint 4 - [SQA] Implementasi Audit Trail Log Otomatis (Event Observer) | Audit / SQA | Muhammad Farras A.A | Medium | 2026-11-25 | 2026-12-02 | 8 Hari | To Do | 0%
5.2 | PBL-30 | Sprint 4 - [SQA] Uji Beban & Penyusunan Dokumen Pengujian Perangkat Lunak (Test Plan & Report) | QA / Test | Muhammad Farras A.A | High | 2026-12-01 | 2026-12-08 | 8 Hari | To Do | 0%
5.3 | PBL-30b | User Acceptance Testing (UAT) dengan Calon Pengguna F&B | QA / UAT | Umi Maharani | High | 2026-12-05 | 2026-12-12 | 8 Hari | To Do | 0%
5.4 | PBL-31 | Sprint 4 - [Doc] Penyusunan Laporan Akhir PBL, User Manual Book & Poster | Documentation | Neyza Ratu Anastasya | Medium | 2026-12-01 | 2026-12-18 | 18 Hari | To Do | 0%
5.5 | PBL-31b | Finalisasi Laporan Akhir PBL, Pembuatan Video Demo & Gelar Karya | Dissemination | Seluruh Tim | Highest | 2026-12-12 | 2026-12-24 | 13 Hari | To Do | 0%
KETERANGAN WARNA GANTT CHART:
Selesai (Done) - 100%
Sedang Berjalan (In Progress)
Rencana Mendatang (To Do)